College of Professional Studies, Northeastern University

PJM 6015: PROJECT RISK MANAGEMENT

Instructor: Professor Kristen Drobnis

Group Assignment (GA) 4: Scope Statement Document

Project Organization:

| Team Member | Team Role |
| --- | --- |
| Ruisi Meng | Project Manager |
| Mophy Sharma | Recorder |
| Aastha Motwani | Supporter |
| Qingyu Sha | Supporter |
| Elizabeth Cohn | Facilitator |

| Project Description: | Atrium Hospitality is a leading hospitality and asset management company with 83 hotels located in 29 states. We work with our properties to renovate existing guest rooms, lobby spaces and meeting space areas on schedule and within budget when needed. We help hotels improve overall organizational performance and customer occupancy. |
| --- | --- |
| Project Objectives: | Our major goal is to renovate the hotel in order to give a better environment for our customers. The renovation project will be completed within the projected budget of $5 million by the end of December 2023. |

| Project Stakeholders: | - Internal Stakeholders - Project Manager - Product Designers - Product Managers - External Stakeholders: - Hotel Staff - Company Lawyer - Local Government Agencies - Suppliers |
| --- | --- |
| Available Resources: | - Personnel: - Project Manager, Development Team, Renovation workers, Interior Designer - Financial Resources: - Spending plan and funding for the project. - Material Resources: - Machinery, tools, and supplies, Furniture, Artifacts - Time resources: - Project Timeline and Timeframe, Deadlines |

1.0 PROJECT DELIVERABLES

- Project Documentation - Research - Design - Renovation - Receive final sponsor sign off - Close Project

2.0 PROJECT MILESTONES

WBS CODE 4.11 5.1.4 5.2.4 5.3 6.6 7.2.35 7.3.4 7.4.5 7.5 8 9.1.3 9.4; MILESTONE Project Documentation Complete Compset Research Complete Location Reserch Complete Research Complete Design Complete Guestroom Renovation Complete Lobby Renovation Complete Meeting Space Renovation Complete Renovation Complete Sponsor Sign Off Lessons Learned Complete Project Complete; DEADLINE Fri 6/24/22 Thu 7/7/22 Thu 7/7/22 Thu 7/7/22 Tue 7/19/22 Mon 9/4/23 Tue 11/28/23 Fri 12/1/23 Fri 12/1/23 Fri 12/1/23 Thu 12/7/23 Wed 12/13/23.

3.0 USER ACCEPTANCE CRITERIA

1. Guests can get an overall good customer experience about hotel renovation. 2. Operations create buffer zones between the guest and work area 3. The paint quality cannot cause harm to the human body 4. Operations update HAVC (Heat, Air Ventilation and colling) 5. Adheres to sponsor's design decision 6. Overall room furniture comfort is improved (mattress, sofa, chairs)

4.0 PROJECT BOUNDARIES

- The Project should start by 4/11/2022 and end by 12/2023.

5.0 PROJECT CONSTRAINTS

- Budget Constraints- The budget should not exceed $5 million. - Must be completed by December 2023 - The room noise test meets the standard. - in order to maintain guest satisfaction - Ensure the health and absolute safety of the local population and all site staff, minimizing the impact on the site environment. - Installation and moving of furniture and other supplies to established locations.

6.0 APPROVAL REQUIREMENTS

- Project contract. - Scope document. - Project plan. - Resource allocation sheet. - Construction land approval procedures