## Risk Register
Risk Number |  |  |  |  | Risk Analysis | [8 empty] | Risk Response Plan | [9 empty] | Risk Monitoring and Controlling
Risk Number | Identify By | Category | Risk Owner | Trigger | Qualitatitive Analysis | [6 empty] | Quantitative Analysis | Risk Action | Risk Response | Detail of Response | Integration with Project Plan | Cost of Response | Reassessment of Risk |  | Contingency Plan | Secondary Risk | Secondary Risk Analysis | Secondary Risk Response | Risk Status
[5 empty] | (The Risk of) | Reasoning (Caused by) | Impact (Resulting in) | Impact | Probability Score | Impact Score | Risk Score | EMV-Cost | [5 empty] | Probability | Impact |  | Risk introduced based on Risk Response
1 |  | Staff | TM 1 | Volunteer sign up is low by mid-point of activity | Hotel Operation Team cannot clear out to three guestroom floors at 3 days as Project Team required | The hotel does not have enough rooms for customers who need to change (especially on holidays) and the customer refuses the option to change rooms. | Guestroom schedule can be delayed or shut down, incurring additional costs. | Schedule of increase in 5 days and cost of $7,500 | 5 | 1 | 5 | Probability = 5 Impact = $7,500 EMV = $3,750 | Response required | Mitigate | Advertise in local paper, reach out to local employers to find volunteers | Add work to WBS/activity list/ estimate/ schedule | 100 | Low | High | Hire mentors | May not get qualified volunteers | Probability - Low Impact - High | Ensure there are clear requirements for mentoring job, cancellation clause in contract. Consider using college students as a next step. | Open
2 |  | Staff | TM 1 | Volunteer sign up is low by mid-point of activity | Material obtained by the supplier was not matching with the ordered material and the material sent by the supplier was also not meeting our quality standards. | Mistake was made by supplier during the time of dispatch of the materials which were not matching the ordered items and quality as well. | Delay of 10-15 days in the schedule was experienced | Schedule was increased for 10 to 15 days and cost of $10,000 was increased. | 5 | 2 | 10 | Probability = 5 Impact = $10,000 EMV = $5000 | Response required | Mitigate | Advertise in local paper, reach out to local employers to find volunteers | Add work to WBS/activity list/ estimate/ schedule | 100 | Low | High | Hire mentors | May not get qualified volunteers | Probability - Low Impact - High | Ensure there are clear requirements for mentoring job, cancellation clause in contract. Consider using college students as a next step. | Open
3 |  | Staff | TM 1 | Volunteer sign up is low by mid-point of activity | An older generation of the in-room assistant (Alexa) being installed. | The company who makes the in-room assistant (Amazon) released a new version of the device ahead of schedule and the price of the older version decreased. | The cost of the technology materials for the guest room refurbishment decreasing. | Cost decrease of $17,000 and no impact on the schedule. | 5 | 1 | 5 | Probability = 5 Impact = $17,000 EMV = $8,500 | Response required | Mitigate | Advertise in local paper, reach out to local employers to find volunteers | Add work to WBS/activity list/ estimate/ schedule | 100 | Low | High | Hire mentors | May not get qualified volunteers | Probability - Low Impact - High | Ensure there are clear requirements for mentoring job, cancellation clause in contract. Consider using college students as a next step. | Open
Note on F4: Mophy Sharma:

## Risk Calculation Sheet
Probability of Occurrence
Very Unlikely | 1
Somewhat unlikely | 3
50-50 possibility | 5
Somewhat likely | 7
Very likely | 9
Original Heat Map
9
Impact of Risk |  | Costs | Schedule | Scope | Quality | 7
Very Low | 1 | 0 - 50k | 0 - 5 | Scope impact barely discernable | Minor defects in production | 5 | 1,3 | 2
Somewhat Low | 2 | 51-150k | 6 to 16 | Minor areas of scope impaired | Small number of moderate defects in prod | 3
Moderate | 4 | 151-250k | 17 to 20 | Many minor areas of scope impaired | Moderate number of moderate defects in prod | 1
Somewhat High | 6 | 251-350k | 21 to 28 | Major areas of scope impaired | High number of moderate defects in prod |  | 1 | 2 | 4 | 6 | 8 | 9
High | 8 | 351-499k | 29 to 41 | Scope reduction unacceptable | Major defects in prod
Extremely High | 9 | $500K+ | 42 days+ | Final product undeliverable or useless | Final product is inoperable
l X I = RS
New Heat Map
Thresholds | [5 empty] | 9
High - 43-81 | [5 empty] | 7 | 3
Medium - 8-42 | [5 empty] | 5
Low - 1-7 | [5 empty] | 3 | 2 | 1
1
[7 empty] | 1 | 2 | 4 | 6 | 8 | 9

## Critical Risk Sheet 1 - DS-RM
Prepared by Denise Sha and Ruisi Meng
Project Name | Embassy Suites DFW Airport North Refurbishment | Division | Construction | Project Impact Phase | Project Execution Phase
Risk Creator | Qingyu Sha | PM | Qingyu Sha | Risk Trigger | The customer does not accept the hotel's remedial measures
Risk Type | Construction | Risk Owner | Customer Service | Review Date | 2022-05-09
Risk # | 1 | Risk Identified By | Ruisi | Max Cost | 10000
Open Date | 2022-07-27 |  |  | Min Cost | 5000
Risk Description |  |  |  | Most Likely Cost | 7500
Hotel Operation Team cannot clear out to three guestroom floors at 3 days as Project Team required |  |  |  |  | Risk Score
|  |  |  | Cost Impact | 1 -- 1
|  |  |  | Schedule Impact | 1 -- 2
|  |  |  | Quality Impact | NA
|  |  |  | Scope Impact | NA
|  |  |  | Probability | 5 -- 3
Preventative Measures (Risk) | [5 empty] | Date Completed
1. Make an announcement online and offline that the hotel guestroom will be renovated from July 27 in 2022 to September 4 in 2023, and that will bring inconvenience to the guests when they try to reserve the rooms on the website or on the phone 2. The hotel offers room upgrades or discount coupons for room reservations or breakfast and dinner for those who need to change rooms. | [5 empty] | 2023-09-04
Contingency Measures (Issue) | [5 empty] | Date Completed
1.The project team and the hotel manager will hold regular meetings to collect and discuss customer complaints about room changes and to develop more possible solutions 2. Customer service was provided with updated guidance to handle customer complaints about chargebacks and replacements, and to document customer feedback reports
Closure Description
If guestroom renovation is done, the problem is resolved.

## Critical Risk 2 - AM-MS
Prepared by Aastha Motwani and Mophy Sharma
Project Name | Embassy DFW Airport North Refurbishment | Division | Supply Chain | Project Impact Phase | Project Execution Phase
Risk Creator | Aastha | PM | Mophy Sharma | Risk Trigger | Material obtained by the supplier was wrong and less quality
Risk Type | Supply Chain | Risk Owner | Supply Chain Manager | Review Date | 2022-05-09
Risk # | 2 | Risk Identified By | Mophy | Max Cost | 15000
Open Date | 2022-05-17 |  |  | Min Cost | 5000
Risk Description |  |  |  | Most Likely Cost | 10000
Material obtained by the supplier was not matching with the ordered material and the material sent by the supplier was also not meeting our quality standards. |  |  |  |  | Risk Score
|  |  |  | Cost Impact | 1---1
|  |  |  | Schedule Impact | 2---1
|  |  |  | Quality Impact | N/A
|  |  |  | Scope Impact | N/A
|  |  |  | Probability | 5---3
Preventative Measures (Risk) | [5 empty] | Date Completed
During the Project Execution Phase of the project, the ordered material will be cross-verified with the supplier by actively monitoring and controlling to ensure that the materials which are getting dispatched from supplier end are same as we ordered. | [5 empty] | 2022-06-17
In Project Execution Phase, buffer time will be created and materials will be ordered few days ahead from the desired time to reduce the delay in schedule.
Contingency Measures (Issue) | [5 empty] | Date Completed
To overcome the delay in the schedule, we will start working with the available material common for refurbishment in different hotel sectors and meets the quality standard of our hotel, and will resume the refurbishment work.
Senior management of the supplier will be informed regarding the situation and necesaary measures will be taken for the further steps of the refurbishment so that further delay in the schedule is not cuased because of such activity.
Closure Description
Once the material is received risk is closed.

## Critical Risk 3 - EC
Prepared by Elizabeth Cohn
Project Name | Embassy Suites DFW Airport North Refurbishment | Division | Purchasing | Project Impact Phase | Construction
Risk Creator | Elizabeth Cohn | PM | Denise Sha | Risk Trigger | The ordering of supplies for the guestroom refurbishment
Risk Type | Technological | Risk Owner | Project Team Member - Technology Orderer | Review Date | 2022-05-09
Risk # | 3 | Risk Identified By | Elizabeth Cohn | Max Cost | -25000
Open Date | 2022-06-27 |  |  | Min Cost | -10000
Risk Description |  |  |  | Most Likely Cost | -17000
The early release of a newer model of the in-room assistant caused the priced of the original model budgeted to drop in comparison. |  |  |  |  | Risk Score
|  |  |  | Cost Impact | 1 --- 1
|  |  |  | Schedule Impact | N/A
|  |  |  | Quality Impact | 1 --- 1
|  |  |  | Scope Impact | N/A
|  |  |  | Probability | 5 --- 7
Preventative Measures (Risk) | [5 empty] | Date Completed
A Google Alert is set up during the Research phase of the project for the in-room assistant in order to get pricing updates and learn immediately if there are major developments with the company producing the device to capitalize on this information during the Construction Phase of the project when it comes to placing the order. | [5 empty] | 2022-06-27
During the Research phase of the project, compare not only models of the same in-room assistant but models across brands to capitilize on any price shifts that occur by purchasing the model that best fits the project and has the potential to save money.
Contingency Measures (Opportunity) | [5 empty] | Date Completed
Should the price of the preferred model drop by a certain percentage, have an alert go out of the risk owner to trigger the purchasing of the in-room assistants in bulk.
Receive pre-approval from the project sponsor during the Design phase to select between one of two or three models (with one being the preferred) to enable the project team to capitalize on any external occurrences that may drive down the price.
Closure Description
The in-room assistants were ordered for the project and this risk was closed.